## Directives
Strategic Action directed by Honorable Supreme Court Order dated 14.09.2016 in Civil Writ Petition No. 95/2012 (Devika Biswas vs UOI)
| Action | Timeline
1 | Upload list of empaneled sterilization providers and QAC members with their names and full particulars in the state website, to be linked to the website of MoHFW, GoI
1.1 | State to prepare and upload list as per annexure | 31.10.2016
1.2 | State to send link to MOHFW GoI | 04.11.2016
1.3 | State to update list | Quarterly | Mar | Jun | Sep | Dec
1.4 | State to submit status of empaneled providers (performing and non performing as per annexure | 31.12.2016
2 | Ensure that consent forms and post operative cards are translated into local language and clients consent is taken after explanation
2.1 | Sterilization consent form translated | 15.10.2016
2.2 | Forms available in all facilities | 20.10.2016
2.3 | QAC to ensure above formats are used correctly | Ongoing
3 | Upload list of QAC members with their names and full particulars in the state website, to be linked to the website of MoHFW, GoI
3.1 | State to prepare and upload separate list of SQAC, SISC, DQAC, DISC as per annexure | 20.10.2016
3.2 | State to send link to MOHFW GoI | 04.11.2016
3.3 | State to update list | Quarterly | Mar | Jun | Sep | Dec
4 | Prepare and upload biannual and annual report card to state website, linked to MOHFW GoI website
4.1 | State to timely submit the quarterly progress | Quarterly | Jan | Apr | Jul | Oct
4.2 | State to prepare 6 monthly and annual report on meetings, enquiries conducted, remedial actions | Biannual | Apr | Oct
4.3 | State to upload 6 months report on state website and link to MOHFW GoI | 20.11.2016
4.4 | State to upload annual report on state website and link to MOHFW GoI | 15.04.2016
5 | Prepare annual reort on death audits, claims submitted and rejected with reasons for deaths. complications and failures
5.1 | SQAC/ SISC/ DQAC/ DISC to conduct audts regularly | Ongoing
5.2 | State to include information of death audits in annual report | 15.04.2016
5.3 | State to timely submit the quarterly FPIS data | Quarterly | Jan | Apr | Jul | Oct
5.4 | State to include information of all FPIS data in annual report | 15.04.2016
6 | Quantum of compensation fixed fixed under FPIS may be doubled with balance being pid from state health budget
6.1 | State should double the compensation amount under FPIS (additions from state budget) | 01.01.2017
7 | State should phase out camps over 3 years and provide Fixed Day Services
7.1 | Discontinue traditional camp (where facility has no OT) | 10.10.2016
7.2 | State to develop static centres for sterilization services as per annexure
7.3 | State to submit DAP and line list of high case load facilities as per DAP format | 30.11.2016
7.4 | State to submit district wise progress report on DAP to GoI | 01.03.2017
8 | Ensure strengthening PHC appropiately for FP services
8.1 | State/ Districts to ensure provision of all FP services as per facility level | Ongoing
8.2 | State/ Districts to ensure provision of PPFP services specifically PPIUCD at all delivery facilities | Ongoing
8.3 | State/ Districts to ensure structured roll out of new contraceptives as per GoI guidelinnes | Ongoing
8.4 | State/ Districts to ensure provision of PAS as per GoI guidelines and provide quarterly reports to GoI | Quarterly | Jan | Apr | Jul | Oct
8.5 | State/ Districts to ensure FP logistics and supply chain management as per GoI guidelines | 30.10.2016
9 | Ensure target free approach for FP services
9.1 | Map operational facilities in districts and calculate facility/ district wise ELA foor logistics and budgets | 10.10.2016
9.2 | State to discontinue area wise reporting immediately | 10.10.2016
10 | Implement decisions of meetings of 15th May 2016, 17th Nov 2015 and National FP Summit 5th - 6th April 2016
10.1 | State to facilitate Annual Review Workshopsby GoI on FP quality parameters and performance | 30.11.2016
10.2 | State to plan for roll out of new contraceptives as per DAP format | 30.12.2016
11 | Disseminate and ensure strict adherence to updated guidelines of GoI
| State to print and ensure GoI manuals and guidelines in all districts | 31.03.2017
| State to conduct quarterly divisional reviews for FP, focus on quality | Quarterly | Mar | Jun | Sep | Dec

## Timeline
Strategic Action directed by Honorable Supreme Court Order dated 14.09.2016 in Civil Writ Petition No. 95/2012 (Devika Biswas vs UOI)
Action | Activities | Timeline
October. 2016
Prepare and upload biannual and annual report card | State to timely submit the quarterly progress | 2016-10-01
Prepare and upload biannual and annual report card | State to prepare 6 monthly and annual report on meetings, enquiries conducted, remedial actions | 2016-10-01
Prepare annual reort on death audits, claims submitted and rejected | State to timely submit the quarterly FPIS data | 2016-10-01
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure provision of PAS as per GoI guidelines and provide quarterly reports to GoI | 2016-10-01
State should phase out camps over 3 years and provide FDS | Discontinue traditional camp (where facility has no OT) | 10.10.2016
Ensure target free approach for FP services | Map operational facilities in districts and calculate facility/ district wise ELA foor logistics and budgets | 10.10.2016
Ensure target free approach for FP services | State to discontinue area wise reporting immediately | 10.10.2016
Consent forms and post operative cards are translated into local language | Sterilization consent form translated | 15.10.2016
Consent forms and post operative cards are translated into local language | Forms available in all facilities | 20.10.2016
Upload list of QAC members with their names and full particulars | State to prepare and upload separate list of SQAC, SISC, DQAC, DISC as per annexure | 20.10.2016
Upload list of empaneled sterilization providers | State to prepare and upload list as per annexure | 31.10.2016
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure FP logistics and supply chain management as per GoI guidelines | 30.10.2016
NOvember. 2016
Upload list of empaneled sterilization providers | State to send link to MOHFW GoI | 04.11.2016
Upload list of QAC members with their names and full particulars | State to send link to MOHFW GoI | 04.11.2016
Prepare and upload biannual and annual report card | State to upload 6 months report on state website and link to MOHFW GoI | 20.11.2016
State should phase out camps over 3 years and provide FDS | State to submit DAP and line list of high case load facilities as per DAP format | 30.11.2016
Implement decisions of high level meetings | State to facilitate Annual Review Workshopsby GoI on FP quality parameters and performance | 30.11.2016
December. 2016
Upload list of empaneled sterilization providers | State to update list | 2016-12-01
Upload list of QAC members with their names and full particulars | State to update list | 2016-12-01
Disseminate and ensure strict adherence to updated guidelines of GoI | State to conduct quarterly divisional reviews for FP, focus on quality | 2016-12-01
Implement decisions of high level meetings | State to plan for roll out of new contraceptives as per DAP format | 30.12.2016
Upload list of empaneled sterilization providers | State to submit status of empaneled providers (performing and non performing as per annexure | 31.12.2016
January. 2017
Prepare and upload biannual and annual report card | State to timely submit the quarterly progress | 2017-01-01
Prepare annual reort on death audits, claims submitted and rejected | State to timely submit the quarterly FPIS data | 2017-01-01
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure provision of PAS as per GoI guidelines and provide quarterly reports to GoI | 2017-01-01
Quantum of compensation fixed fixed under FPIS may be doubled | State should double the compensation amount under FPIS (additions from state budget) | 01.01.2017
Match. 2017
Upload list of empaneled sterilization providers | State to update list | 2017-03-01
Upload list of QAC members with their names and full particulars | State to update list | 2017-03-01
Disseminate and ensure strict adherence to updated guidelines of GoI | State to conduct quarterly divisional reviews for FP, focus on quality | 2017-03-01
State should phase out camps over 3 years and provide FDS | State to submit district wise progress report on DAP to GoI | 01.03.2017
Disseminate and ensure strict adherence to updated guidelines of GoI | State to print and ensure GoI manuals and guidelines in all districts | 31.03.2017
April. 2017
Prepare and upload biannual and annual report card | State to timely submit the quarterly progress | 2017-04-01
Prepare and upload biannual and annual report card | State to prepare 6 monthly and annual report on meetings, enquiries conducted, remedial actions | 2017-04-01
Prepare annual reort on death audits, claims submitted and rejected | State to timely submit the quarterly FPIS data | 2017-04-01
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure provision of PAS as per GoI guidelines and provide quarterly reports to GoI | 2017-04-01
Prepare and upload biannual and annual report card | State to upload annual report on state website and link to MOHFW GoI | 15.04.2017
Prepare annual reort on death audits, claims submitted and rejected | State to include information of death audits in annual report | 15.04.2017
Prepare annual reort on death audits, claims submitted and rejected | State to include information of all FPIS data in annual report | 15.04.2017
June. 2017
Upload list of empaneled sterilization providers | State to update list | 2017-06-01
Upload list of QAC members with their names and full particulars | State to update list | 2017-06-01
Disseminate and ensure strict adherence to updated guidelines of GoI | State to conduct quarterly divisional reviews for FP, focus on quality | 2017-06-01
July. 2017
Prepare and upload biannual and annual report card | State to timely submit the quarterly progress | 2017-07-01
Prepare annual reort on death audits, claims submitted and rejected | State to timely submit the quarterly FPIS data | 2017-07-01
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure provision of PAS as per GoI guidelines and provide quarterly reports to GoI | 2017-07-01
September. 2017
Upload list of empaneled sterilization providers | State to update list | 2017-09-01
Upload list of QAC members with their names and full particulars | State to update list | 2017-09-01
Disseminate and ensure strict adherence to updated guidelines of GoI | State to conduct quarterly divisional reviews for FP, focus on quality | 2017-09-01
Ongoing
Consent forms and post operative cards are translated into local language | QAC to ensure above formats are used correctly | Ongoing
Prepare annual reort on death audits, claims submitted and rejected | SQAC/ SISC/ DQAC/ DISC to conduct audts regularly | Ongoing
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure provision of all FP services as per facility level | Ongoing
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure provision of PPFP services specifically PPIUCD at all delivery facilities | Ongoing
Ensure strengthening PHC appropiately for FP services | State/ Districts to ensure structured roll out of new contraceptives as per GoI guidelinnes | Ongoing
State should phase out camps over 3 years and provide FDS | State to develop static centres for sterilization services as per annexure

## 2.1 ML
Annexure- 2.1A Format for listing empaneled providers for uploading in State website
Empanelment List for Minilap
State | BIHAR
Year | 2016-17
S.N | District | Name of empanelled provider | Qualification (MBBS/MS-Gyne or Surgery/DGO etc) | Designation | Type of facility posted (DH, SDH, RH, PHC) | Postal address of facility (Name of facility where empanelled provider is posted) | Contact number
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## 2.1 NSV
Annexure- 2.1 B Format for listing empaneled providers for uploading in State website
Empanelment List for NSV
State | BIHAR
Year | 2016-17
S.N | District | Name of empanelled provider | Qualification (MBBS/MS-Gyne or Surgery/DGO etc) | Designation | Type of facility posted (DH, SDH, RH, PHC) | Postal address of facility (Name of facility where empanelled provider is posted) | Contact number
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## 2.2 Provider performance
Annexure-2.2 Line listinng of Sterilization trained/ Empanelled Providers
Empanelment List for NSV
State | BIHAR
Year | 2016-17
S.N | District | Name of trained/ empanelled provider | Qualification | Place of posting (Name of facility and level) | Contact number | Trained/ Empanelled for |  | Services provided in last one year |  |  |  | Remarks
[6 empty] | Minilap | NSV | No. of Minilap performed | If not performed surgery, please quote the reason | No. of NSV performed | If not performed surgery, please quote the reason
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## 2.3 QAC Members
Annexure2.3: Format for listing DQAC and DISC members in State/UT website
State | BIHAR | District
Year | 2016-17
Type of Committee (DQAC/DISC)
S.N | Name of Member | Designation in the Committee (Chairperson/Voice Chairperson /Convener/Member Secretary/Member) | Designation in the District (DM/Civil Surgeon/ACMO/DPM//Empaneled Gynecologist/Surgeon etc.) | Member Since(Month/Year) | Address | Contact number
1
2
3
4
5
6
7
8
9
10

## 2.4 Annual Biannual Report
Annexure-2.4
Report Format
State | BIHAR
Year | 2016-17
State
Report Type: (Annual/Biannual)
Reporting Period
Family Planning Performance
Services | Q1 | Q2 | Q3 | Q4 | Total
Interval Minilab
Laparoscopy
PPS
Female Sterilization
Male Sterilization
IUCD
PPIUCD
PPIUCD Acceptance*
*Out of total public health institutional deliveries
ASHA Scheme Performance:
Services | Q1 | Q2 | Q3 | Q4 | Total
HDC (% distribution of condom and ECP)
ADY Schemes
PTK Utilization
Status of Functionality of QAC
Number of meetings held.
Frequency of meetings held (Quarterly/half yearly):
Minutes of the meetings prepared(Yes/No)
Number of Death, Complication and failure reported
Number of Enquiries conducted for each category
Remedial steps taken

## 2.5FPIS Status
Status of FPIS Claim | [12 empty] | Annexure-2.5
State |  | BIHAR
Year |  | 2016-17
S.N | Name of District | Fresh New Claims submitted in 2016-17 |  |  | Outstanding cases from 2015-16 |  |  | Claims Paid (2016-17) | [5 empty] | Claims Rejected (2016-17) | [5 empty] | Outstanding claimms till 31st March 2017
|  | Complication | Death | Failure | Complication | Death | Failure | Complication | Amount Paid | Death | Amount Paid | Failure | Amount Paid | Complication | Amount | Death | Amount | Failure | Amount | Complication | Amount | Death | Amount | Failure | Amount
Specify Reasoms for claim rejection (death/ Complication/ Failure)
Status of Death Audits
State | BIHAR
Year | 2016-17
Name of District | No. of Deaths Reported |  | No. of Death Audits Conducted |  | No. of deaths attributed to Sterilization |  | Reason of Death |  | Action Taken